## PSAP 1
NG911 sample GIS Data Remediation B&P Basis of Estimate | [7 empty] | Bid | [6 empty] | Actual
Work Package | provided by Randall
Name of PSAP | Finney County | Prepared | [6 empty] | Prepared
Name of PM | John Finney | Revised | [6 empty] | Revised
Contact PM | 816-245-8585
|  | Bid Estimate | [6 empty] | Actual Cost
WBS | Deliverable | Resource | Start | Finish | # mh | Rate ($) | Cost ($) |  | Resource | Start | Finish | # mh | Rate ($) | Cost ($)
| Prepare Project Plan | [5 empty] | 0 | [6 empty] | 0
| Review and analyze Data Analysis / Report | [5 empty] | 0 | [6 empty] | 0
| Resolve discepancies Data Analysis / Report | [5 empty] | 0 | [6 empty] | 0
| Remediate Data | [5 empty] | 0 | [6 empty] | 0
| Prepare/submit Data Gap Remediation Report | [5 empty] | 0 | [6 empty] | 0
| Assist QA vendor interpreting remediated data | [5 empty] | 0 | [6 empty] | 0
other
| Total Labor |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
[5 empty] | # trips | $/trip | T&L |  |  |  |  | # trips | $/trip | T&L
| Travel to | [5 empty] | 0 | [6 empty] | 0
| Travel to | [5 empty] | 0 | [6 empty] | 0
other
| Total Travel |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
| Grand Total | [5 empty] | 0 | [6 empty] | 0
Description of Services (how accomplished):
1
2
3

## PSAP 2
NG911 sample GIS Data Remediation B&P Basis of Estimate | [7 empty] | Bid | [6 empty] | Actual
Work Package | provided by Randall
Name of PSAP | Finney County | Prepared | [6 empty] | Prepared
Name of PM | John Finney | Revised | [6 empty] | Revised
Contact PM | 816-245-8585
|  | Bid Estimate | [6 empty] | Actual Cost
WBS | Deliverable | Resource | Start | Finish | # mh | Rate ($) | Cost ($) |  | Resource | Start | Finish | # mh | Rate ($) | Cost ($)
| Prepare Project Plan | [5 empty] | 0 | [6 empty] | 0
| Review and analyze Data Analysis / Report | [5 empty] | 0 | [6 empty] | 0
| Resolve discepancies Data Analysis / Report | [5 empty] | 0 | [6 empty] | 0
| Remediate Data | [5 empty] | 0 | [6 empty] | 0
| Prepare/submit Data Gap Remediation Report | [5 empty] | 0 | [6 empty] | 0
| Assist QA vendor interpreting remediated data | [5 empty] | 0 | [6 empty] | 0
other
| Total Labor |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
[5 empty] | # trips | $/trip | T&L |  |  |  |  | # trips | $/trip | T&L
| Travel to | [5 empty] | 0 | [6 empty] | 0
| Travel to | [5 empty] | 0 | [6 empty] | 0
other
| Total Travel |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
| Grand Total | [5 empty] | 0 | [6 empty] | 0
Description of Services (how accomplished):
1
2
3

## PSAP 3
NG911 sample GIS Data Remediation B&P Basis of Estimate | [7 empty] | Bid | [6 empty] | Actual
Work Package | provided by Randall
Name of PSAP | Finney County | Prepared | 2014-04-10 | [5 empty] | Prepared
Name of PM | John Finney | Revised | 2014-04-16 | [5 empty] | Revised
Contact PM | 816-245-8585
|  | Bid Estimate | [6 empty] | Actual Cost
WBS | Deliverable | Resource | Start | Finish | # mh | Rate ($) | Cost ($) |  | Resource | Start | Finish | # mh | Rate ($) | Cost ($)
| Prepare Project Plan | [5 empty] | 0 | [6 empty] | 0
| Review and analyze Data Analysis / Report | [5 empty] | 0 | [6 empty] | 0
| Resolve discepancies Data Analysis / Report | [5 empty] | 0 | [6 empty] | 0
| Remediate Data | [5 empty] | 0 | [6 empty] | 0
| Prepare/submit Data Gap Remediation Report | [5 empty] | 0 | [6 empty] | 0
| Assist QA vendor interpreting remediated data | [5 empty] | 0 | [6 empty] | 0
other
| Total Labor |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
[5 empty] | # trips | $/trip | T&L |  |  |  |  | # trips | $/trip | T&L
| Travel to | [5 empty] | 0 | [6 empty] | 0
| Travel to | [5 empty] | 0 | [6 empty] | 0
other
| Total Travel |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
| Grand Total | [5 empty] | 0 | [6 empty] | 0
Description of Services (how accomplished):
1
2
3

## Sample
NG911 sample GIS Data Remediation B&P Basis of Estimate | [7 empty] | Bid | [6 empty] | Actual
Work Package | provided by Randall
Name of PSAP | Finney County | Prepared | 2014-04-10 | [5 empty] | Prepared
Name of PM | John Finney | Revised | 2014-04-16 | [5 empty] | Revised
Contact PM | 816-245-8585
|  | Bid Estimate | [6 empty] | Actual Cost
WBS | Deliverable | Resource | Start | Finish | # mh | Rate ($) | Cost ($) |  | Resource | Start | Finish | # mh | Rate ($) | Cost ($)
| Prepare Project Plan | John | 2014-04-20 | 2014-04-25 | 15 | 100 | 1500 |  | Rex | 2014-04-20 | 2014-04-25 | 10 | 100 | 1000
| Review and analyze Data Analysis / Report | Rex | 2014-05-01 | 2014-05-30 | 135 | 100 | 13500 |  | John | 2014-05-01 | 2014-05-30 | 120 | 100 | 12000
| Resolve discepancies Data Analysis / Report | Bill | 2014-05-20 | 2014-05-30 | 10 | 100 | 1000 |  | Jack | 2014-05-20 | 2014-05-30 | 18 | 100 | 1800
| Remediate Data | Rex | 2014-05-15 | 2014-06-30 | 180 | 100 | 18000 |  | Harry | 2014-05-15 | 2014-06-30 | 200 | 100 | 20000
| Prepare/submit Data Gap Remediation Report | John | 2014-06-20 | 1931-06-01 | 10 | 100 | 1000 |  | Rex | 2014-06-20 | 1931-06-01 | 8 | 100 | 800
| Assist QA vendor interpreting remediated data | Bill | 2014-06-10 | 2014-06-15 | 4 | 100 | 400 |  | John | 2014-06-10 | 2014-06-15 | 3 | 100 | 300
other
| Total Labor |  |  |  | 354 |  | 35400 |  |  |  |  | 359 |  | 35900
[5 empty] | # trips | $/trip | T&L |  |  |  |  | # trips | $/trip | T&L
| Travel to | Rex | 2014-05-20 | 2014-05-20 | 1 | 350 | 350 |  | Bill | 2014-05-22 | 2014-05-23 | 2 | 300 | 600
| Travel to | Rex | 2014-06-01 | 2014-06-02 | 1 | 420 | 420 |  | Bill | 2014-06-05 | 2014-06-06 | 1 | 450 | 450
| Travel to | Rex | 2014-06-10 | 2014-06-11 | 1 | 465 | 465 |  | Bill |  |  | 0 | 0 | 0
| Total Travel |  |  |  | 3 |  | 1235 |  |  |  |  | 3 |  | 1050
| Grand Total | [5 empty] | 36635 | [6 empty] | 36950
Description of Services (how accomplished):
1 | note: this is a sample B&P and is not intended to provide guidance or direction. Vendor discretion advised.
2
3